## Project Plan
Phase | Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Owner | Status/Notes
Planning | Project Proposal | Week 1: Done | Abdelhalim | Completed
Planning | Requirements Gathering (SRS) | Week 1: In Progress; Week 2: In Progress | Youssef
Design | Database Schema Design | Week 2: Planned | Mohamed
Design | API Design (Swagger Docs) | Week 2: In Progress; Week 3: In Progress | Abdelmageed
Backend | Core Infrastructure Setup | Week 3: In Progress; Week 4: In Progress | Abdelmageed
Frontend | UI Development | Week 3: In Progress; Week 4: In Progress; Week 5: Planned | Youssef
Testing | Integration & System Testing | Week 5: Planned; Week 6: Planned | Team
Documentation | Final Documentation | Week 5: Planned; Week 6: Planned | Abdelhalim